## Bug_Report
Issue Type | Issue key | Issue id | Summary | Assignee | Reporter | Priority | Status | Created | Updated | Due date
Bug | SCRUM-152 | 10446 | Defect_Reg_02_Cart accepts Character value | Developer-1 | vaishnavi sainathan | Medium | In Progress | 2026-02-27 09:26 | 2026-03-05 15:30 | 2026-04-17
Bug | SCRUM-151 | 10444 | Defect_Reg_01_Cart accepts decimal quantity value | Developer-1 | vaishnavi sainathan | Medium | In Review | 2026-02-27 09:20 | 2026-03-05 15:31 | 2026-04-17
Bug | SCRUM-150 | 10410 | BUG_CUSTOMER_INFO_06_Confirmation message was not displayed on changing the Personal details | Developer-1 | vaishnavi sainathan | Low | In Review | 2026-02-26 13:49 | 2026-03-05 15:32 | 2026-04-03
Bug | SCRUM-149 | 10408 | BUG_CHECKOUT_05_No Error message is displayed when Zip code field is left blank | Developer-1 | vaishnavi sainathan | Medium | In Progress | 2026-02-26 13:41 | 2026-03-05 15:33 | 2026-03-20
Bug | SCRUM-148 | 10406 | BUG_CART_08_Character quantity resets to 1 without validation message | Developer-1 | vaishnavi sainathan | Medium | In Review | 2026-02-26 13:34 | 2026-03-05 15:33 | 2026-03-20
Bug | SCRUM-147 | 10404 | BUG_CART_07_Decimal quantity resets to 1 without validation message | Developer-1 | vaishnavi sainathan | Medium | In Progress | 2026-02-26 13:29 | 2026-03-05 15:34 | 2026-03-20
Bug | SCRUM-146 | 10402 | BUG_CART_04_Based on the number of items in the cart ,Tax amount is not calculated | Developer-1 | vaishnavi sainathan | High | In Progress | 2026-02-26 12:43 | 2026-03-05 15:34 | 2026-03-19
Bug | SCRUM-145 | 10400 | BUG_SEARCH_03_The user is not able to change the color and size of the displayed product | Developer-1 | vaishnavi sainathan | Medium | In Progress | 2026-02-26 12:33 | 2026-03-05 15:34 | 2026-03-19
Bug | SCRUM-144 | 10398 | BUG_SEARCH_02_User is not able to add the product "Elite Desktop PC" to the cart | Developer-1 | vaishnavi sainathan | High | In Review | 2026-02-26 12:26 | 2026-03-05 15:36 | 2026-03-16
Bug | SCRUM-143 | 10396 | BUG_LOGIN_01_User is not logged out after 15 mins of inactive time period | Developer-1 | vaishnavi_Admin | High | In Progress | 2026-02-26 12:00 | 2026-03-05 14:57 | 2026-03-05